Internal Project Brief

A Generalizable Spatio-Temporal Framework for Emerging Infectious Disease Forecasting

Engineering scope · research goals · milestones · deliverables · deadlines

| Audience | Internal — engineering team (implementation lead) |
| --- | --- |
| Purpose | Single reference for what we have decided, what needs to be built, who does what, and by when |
| Duration | 6 weeks, full-time (assume 5 working days/week → 30 working days). Start date: __________ |
| Pricing | Not included — this is an internal working document |
| Target outcome | A reproducible, novel methodological contribution suitable for a high-impact (ISI) journal |

How to read the tags in this document Items are labelled so priorities are unambiguous: [REQUIRED] — a decided, must-deliver requirement (client need or agreed scope). [SUGGESTION] — our recommendation to strengthen the work; follow unless told otherwise, but it is our proposal rather than a fixed client requirement. [OUT OF SCOPE] — deliberately excluded from this engagement.

1. Project overview

We are building a general, disease-agnostic framework for emerging infectious disease forecasting. The architecture is not specialised to any single disease; it learns transferable spatio-temporal representations from data-rich diseases and adapts, with minimal modification, to a data-scarce emerging disease. Data-rich diseases are used to develop and validate the methodology; Ebola is the headline case study demonstrating generalisation to a scarce, real-world emerging disease.

Why it is novel: recent state-of-the-art models are largely single-disease or stay within one disease family, and several explicitly flag cross-disease transferability as open future work. A framework that is disease-agnostic by construction, transfers across diseases, adapts few-shot to a scarce disease, and reports calibrated uncertainty addresses a clear, identifiable research gap.

2. Research goals & objectives

The work is judged against these goals:

- G1 — A disease-agnostic spatio-temporal forecasting architecture operating on a standardised input schema. [REQUIRED]

- G2 — Transferable representations learned across multiple data-rich diseases. [REQUIRED]

- G3 — Demonstrated generalisation to a data-scarce emerging disease (Ebola) via few-shot adaptation. [REQUIRED]

- G4 — Calibrated uncertainty quantification on all forecasts. [REQUIRED]

- G5 — Explainability of forecasts. [REQUIRED]

- G6 — Competitive-or-better performance vs. recent SOTA baselines, re-run under identical conditions. [REQUIRED]

- G7 — A reproducible, submission-ready contribution (code + manuscript). [REQUIRED]

3. Scope — in and out

| In scope | Out of scope |
| --- | --- |
| - Spatio-temporal forecasting (cases / deaths) - Calibrated uncertainty quantification - Explainability of forecasts - Cross-disease transfer & few-shot adaptation - Empirical benchmark + full literature review | ✕ Regional risk stratification ✕ Intervention priority ranking Reason: no agreed ground-truth labels, so they cannot be trained or validated rigorously and would weaken the paper. Natural future extension. |

4. Methodology — what to build

Displaybarcode”Four design pillars, none specific to one disease:

- Disease-agnostic spatio-temporal encoder — temporal + graph components over a standardised schema (normalised incidence, spatial adjacency, generic covariates). [REQUIRED]

- Epidemiology-informed inductive bias — a metapopulation / compartmental-aware component (or physics-informed loss) for data efficiency and generalisation. [SUGGESTION]

- Transferable representation learning with few-shot adaptation — meta-learning / domain-generalisation so the encoder captures disease-invariant dynamics and adapts with minimal data. [REQUIRED]

- Calibrated uncertainty — conformal prediction is recommended (model-agnostic, post-hoc); a Bayesian approach is an alternative but would move UQ into the model build in Week 3. [SUGGESTION]”qr

5. Datasets

- Dengue — primary development disease (large, dense, spatially-resolved). [REQUIRED]

- Influenza — second development disease, to make the “general framework” claim credible (avoids a dengue-only model). [SUGGESTION]

- COVID-19 — optional third development disease for added diversity. [SUGGESTION]

- Ebola — held-out, data-scarce case study for the few-shot generalisation test; assembled from outbreak situation reports. [REQUIRED]

Note for the engineer All diseases must be mapped onto one standardised input schema so the architecture stays disease-agnostic. Run a data audit early (coverage, resolution, missingness) — Ebola data is small, so confirm the usable signal before relying on it.

6. Deliverables (what the client needs)

All deliverables below are required unless tagged otherwise:

- Working, documented framework (source code) operating on the standardised schema

- Benchmark report: reproduced SOTA baselines vs. our framework on identical data

- Literature review / related-work section (structured SOTA comparison, research gap, how our method addresses limitations) — now fully owned by us

- Cross-disease transfer results (leave-one-disease-out)

- Ebola few-shot case study results, with prediction intervals

- Ablation studies + robustness / sensitivity analysis

- Explainability outputs (e.g. SHAP, global + local)

- Submission-ready manuscript (methods, experiments, results, discussion)

- Reproducibility package: code, configs, README, instructions

7. Milestones, tasks & deadlines

Six weekly milestones, full-time. “Target” shows working-day ranges from the agreed start date.

| Week 1 — Benchmark, literature review & problem setup |  |
| --- | --- |
| Target | Days 1–5 |
| Objective | Establish the research gap, the formal problem, and reproducible baselines. |
| Engineer tasks | - Write the full literature review & structured SOTA comparison (now fully ours) [REQUIRED] - Select 4–6 baselines (relevance, recency/impact, method-family coverage, public code, comparability); share shortlist with client before locking [REQUIRED] - Reproduce baselines using official public implementations where available [REQUIRED] - Define the formal problem, evaluation metrics & validation protocol [REQUIRED] - Specify the standardised, disease-agnostic input schema [REQUIRED] |
| Deliverables | - Literature-review / related-work draft - Baseline shortlist + selection rationale - Problem definition & evaluation protocol - Input schema specification |

| Week 2 — Multi-disease data engineering & harmonisation |  |
| --- | --- |
| Target | Days 6–10 |
| Objective | Build clean, harmonised, leak-free datasets. |
| Engineer tasks | - Acquire, parse & clean dengue data [REQUIRED] - Add influenza (and optionally COVID-19) development data [SUGGESTION] - Assemble the Ebola case-study dataset from outbreak situation reports [REQUIRED] - Map all diseases onto the standardised schema; build preprocessing + train/val/test splits [REQUIRED] - Run a data audit (coverage, resolution, missingness) — confirm usable Ebola signal [REQUIRED] |
| Deliverables | - Harmonised multi-disease datasets - Reproducible data pipeline + documentation - Data audit note |

| Week 3 — Core framework build & development training |  |
| --- | --- |
| Target | Days 11–15 |
| Objective | Implement and validate the core model on the data-rich diseases. |
| Engineer tasks | - Implement the disease-agnostic spatio-temporal encoder (temporal + graph) [REQUIRED] - Integrate the epidemiology-informed component [SUGGESTION] - Train on the data-rich diseases + hyperparameter tuning [REQUIRED] - Re-run the selected baselines on the harmonised data; benchmark vs. our framework [REQUIRED] |
| Deliverables | - Working framework (v1) + training code - Benchmark results vs. baselines on development diseases - Technical design note |

| Week 4 — Transferable representations, meta-learning & few-shot adaptation |  |
| --- | --- |
| Target | Days 16–20 |
| Objective | Add the core methodological contribution: transfer + few-shot adaptation. |
| Engineer tasks | - Implement meta-learning / domain-generalisation training [REQUIRED] - Disease-invariant representation learning [REQUIRED] - Leave-one-disease-out transfer evaluation across development diseases [REQUIRED] - Build the few-shot adaptation protocol for an unseen disease [REQUIRED] |
| Deliverables | - Framework (v2) with transfer module - Leave-one-disease-out transfer results - Few-shot adaptation protocol |

| Week 5 — Ebola case study, uncertainty & explainability |  |
| --- | --- |
| Target | Days 21–25 |
| Objective | Demonstrate generalisation to a data-scarce disease, with calibrated uncertainty and explanations. |
| Engineer tasks | - Run the Ebola out-of-distribution few-shot case study [REQUIRED] - Add calibrated uncertainty quantification (conformal recommended) + calibration checks [REQUIRED] - Produce explainability outputs (SHAP global + local) [REQUIRED] - Compile case-study results with prediction intervals [REQUIRED] |
| Deliverables | - Ebola case-study results with uncertainty - Calibration evaluation - Explainability outputs |

| Week 6 — Ablations, robustness, writing & documentation |  |
| --- | --- |
| Target | Days 26–30 |
| Objective | Establish robustness, then produce a submission-ready paper and reproducible release. |
| Engineer tasks | - Ablations: with vs. without epidemiology-informed component; standard vs. meta-learning [REQUIRED] - Robustness / sensitivity analysis; finalise all tables & figures [REQUIRED] - Draft the full manuscript (incl. literature review, methodology, experiments, results, discussion) [REQUIRED] - Finalise source code + README + reproducibility package; submission support [REQUIRED] |
| Deliverables | - Ablation & robustness study - Submission-ready manuscript - Reproducibility package |

Post-submission (separate engagement) Reviewer response & one revision round (point-by-point response, requested re-runs, updated figures/tables) is handled separately after submission and is not part of the 6-week core schedule.

8. Timeline at a glance

| Week | Focus | Days | Cumulative |
| --- | --- | --- | --- |
| W1 | Benchmark, literature review & problem setup | 1–5 | Day 5 |
| W2 | Multi-disease data engineering | 6–10 | Day 10 |
| W3 | Core framework build & training | 11–15 | Day 15 |
| W4 | Transfer, meta-learning & few-shot | 16–20 | Day 20 |
| W5 | Ebola case study, uncertainty & explainability | 21–25 | Day 25 |
| W6 | Ablations, robustness, writing & docs | 26–30 | Day 30 |

Sequencing note Milestones run in dependency order, each building on the previous. Two activities span phases by design: baseline reproduction begins in Week 1 and is re-run on the harmonised data in Week 3 (identical-conditions comparison), and manuscript drafting starts in parallel from Week 4 so Week 6 is assembly and interpretation rather than writing from scratch.

9. Roles & responsibilities

| Party | Responsible for |
| --- | --- |
| Our team (engineering) | All implementation, data engineering, experiments, the full literature review & benchmark, manuscript drafting, and the reproducibility package. |
| Client (Nora) | Direction & feedback, milestone-gate review and sign-off, decisions on target journal and authorship. Note: the client is no longer running a separate benchmark — the full literature review is now ours. |

10. Evaluation & validation protocol

- Baselines re-run under identical conditions (same datasets, splits, preprocessing, metrics, horizon) — the basis of any SOTA claim.

- Development evaluation on the data-rich diseases with standard forecasting metrics.

- Generalisation via leave-one-disease-out transfer, and few-shot adaptation to held-out Ebola.

- Uncertainty reported as calibrated prediction intervals, with calibration checks.

- Ablations isolating the epidemiology-informed component and the meta-learning contribution.

11. Required vs. suggested — quick reference

| Item | Status |
| --- | --- |
| Forecasting + calibrated uncertainty + explainability | Required |
| Disease-agnostic encoder + meta-learning transferable representations | Required |
| Ebola few-shot generalisation case study | Required |
| Full literature review + empirical benchmark (re-run baselines) | Required |
| Dengue as a development disease | Required |
| Adding influenza (and optionally COVID-19) as further development diseases | Suggestion |
| Epidemiology-informed component | Suggestion |
| Conformal UQ (vs. Bayesian alternative) | Suggestion |
| Regional risk stratification / intervention priority ranking | Out of scope |

12. Risks & mitigations

- Ebola data scarcity — confirm usable signal in the Week-2 audit; the design treats Ebola as a few-shot test precisely because the data is thin.

- Tight 6-week schedule — Weeks 3–4 are the densest; protect them by freezing scope and starting the write-up early.

- Baseline reproduction — prefer official code; where none exists, validate a from-scratch reimplementation against the paper’s reported numbers before comparing.

- UQ method choice — decide conformal vs. Bayesian before Week 3, as Bayesian moves UQ into the model build.

13. Definition of done

- Framework runs end-to-end on the standardised schema and is documented

- Our model is benchmarked against the agreed baselines on identical data

- Transfer + few-shot Ebola results produced with calibrated uncertainty

- Ablations and explainability completed

- Manuscript + reproducibility package ready for submission

14. Open questions to confirm before Week 1

- Final development-disease set: dengue + influenza only, or also COVID-19?

- UQ approach: conformal (recommended) or Bayesian?

- Start date and target journal.

- Authorship & IP terms.